## AD DS Buildout Tracker
Phase | Step | What Is Being Done | Run From | Target | What To Do (Command) | Expected Result | Actual Result | Rating
PHASE 0 - PRE-FLIGHT
P0 | 0.1 | Confirm static IP + name resolution | dc01 | dc01 | Get-NetIPConfiguration | Static IP, correct DNS
PHASE 1 - FOREST PROMOTION
P1 | 1.1 | Install AD DS + promote forest (preview) | dc01 | dc01 | .\Install-ADDSForest.ps1 -DomainName lab.local -WhatIf | WhatIf shows role install + promotion
P1 | 1.2 | Promote for real (prompts DSRM) | dc01 | dc01 | .\Install-ADDSForest.ps1 -DomainName lab.local | Promotion succeeds; auto reboot
PHASE 2 - CORE VERIFICATION
P2 | 2.1 | Domain controller diagnostics | dc01 | dc01 | dcdiag /v | All tests passed
P2 | 2.2 | SYSVOL / NETLOGON shares present | dc01 | dc01 | net share | SYSVOL and NETLOGON listed
P2 | 2.3 | DNS SRV records registered | dc01 | dc01 | nslookup -type=SRV _ldap._tcp.lab.local | DC returned
PHASE 3 - HEALTH / FSMO
P3 | 3.1 | Replication + FSMO summary | admin-pc | lab.local | .\Get-ADHealthReport.ps1 -Domain lab.local | Healthy=True; FSMO on dc01
PHASE 4 - INVENTORY
P4 | 4.1 | Baseline directory inventory | admin-pc | lab.local | .\Get-ADInventory.ps1 -OutputFolder .\AD-Inventory | CSVs for users/computers/groups/OUs/GPOs