## Host Buildout Tracker
Phase | Step | What Is Being Done | Run From | Target | What To Do (Command) | Expected Result | Actual Result | Rating
PHASE 0 - PRE-FLIGHT
P0 | 0.1 | Confirm hardware virtualization (SLAT) enabled | hv01 | hv01 | systeminfo ¦ findstr /i "Hyper-V" | All Hyper-V requirements = Yes
P0 | 0.2 | Confirm Windows Server edition/patch level | hv01 | hv01 | Get-ComputerInfo ¦ Select WindowsProductName,OsBuildNumber | Supported Server build
PHASE 1 - ROLE INSTALL
P1 | 1.1 | Install Hyper-V role + host baseline | hv01 | hv01 | .\Install-HyperVHost.ps1 -VmPath D:\VMs -VhdPath D:\VHDs -WhatIf | WhatIf lists role + 4 baseline changes
P1 | 1.2 | Apply for real; reboot | hv01 | hv01 | .\Install-HyperVHost.ps1 -VmPath D:\VMs -VhdPath D:\VHDs | HyperVInstalled=True; RebootPending flagged
P1 | 1.3 | Verify role after reboot | hv01 | hv01 | Get-WindowsFeature Hyper-V | Installed = True
PHASE 2 - VIRTUAL SWITCH
P2 | 2.1 | Create switches from CSV (preview) | hv01 | hv01 | .\New-HyperVVMSwitch.ps1 -Csv .\switches.csv -WhatIf | Each switch listed, none created
P2 | 2.2 | Create switches | hv01 | hv01 | .\New-HyperVVMSwitch.ps1 -Csv .\switches.csv | Switches present; SET team where >1 NIC
P2 | 2.3 | Confirm management connectivity retained | admin-pc | hv01 | Test-NetConnection hv01 -Port 5985 | TcpTestSucceeded = True
PHASE 3 - VM BUILD
P3 | 3.1 | Build Gen2 lab VMs from CSV | hv01 | hv01 | .\New-HyperVLabVM.ps1 -Csv .\vms.csv | VMs created; Gen2; dynamic memory set
P3 | 3.2 | Confirm Secure Boot + vTPM where requested | hv01 | hv01 | Get-VMFirmware *; Get-VMSecurity * | SecureBoot On; TPM enabled per CSV
PHASE 4 - LIVE MIGRATION / REPLICA
P4 | 4.1 | Validate live migration between hosts | hv01 | hv02 | Move-VM -Name test01 -DestinationHost hv02 | VM runs on hv02, no downtime
P4 | 4.2 | Configure + verify Hyper-V Replica | hv01 | hv02 | .\Get-HyperVReplicationStatus.ps1 -ComputerName hv01,hv02 | Health = Normal for replicated VMs
PHASE 5 - INVENTORY / CAPACITY
P5 | 5.1 | Capture host inventory | admin-pc | hv01,hv02 | .\Get-HyperVInventory.ps1 -ComputerName hv01,hv02 | CSV with one row per VM
P5 | 5.2 | Capture capacity/headroom | admin-pc | hv01,hv02 | .\Get-HyperVHostCapacity.ps1 -ComputerName hv01,hv02 | vCPU:pCPU + mem commit reported