## AVD Validation Tracker
Phase | Step | What Is Being Done | Run From | Target | What To Do (Command) | Expected Result | Actual Result | Rating
PHASE 0 - PRE-FLIGHT
P0 | 0.1 | Confirm subscription + region quota | admin-pc | Azure | az vm list-usage -l centralus -o table | Dsv4 family cores available
P0 | 0.2 | Confirm Entra groups + licensing | admin-pc | Entra | az ad group show --group grp-avd-users | Group exists; P1 where CA used
PHASE 1 - DEPLOY
P1 | 1.1 | Bicep what-if | admin-pc | Azure | az deployment sub what-if -f bicep/main.bicep -p bicep/params/cust-lab.bicepparam | Expected resource set, no surprises
P1 | 1.2 | Deploy stack | admin-pc | Azure | az deployment sub create -f bicep/main.bicep -p bicep/params/cust-lab.bicepparam | Deployment succeeds
PHASE 2 - IDENTITY / SSO
P2 | 2.1 | Enable AVD SSO | admin-pc | Entra | .\scripts\enable-avd-sso.ps1 | Target device groups configured
P2 | 2.2 | Conditional Access / MFA | admin-pc | Entra | .\scripts\conditional-access-mfa.ps1 | CA policy present (report-only first)
PHASE 3 - PROFILE / STORAGE
P3 | 3.1 | Entra Kerberos on storage | admin-pc | Azure Files | .\scripts\enable-storage-kerberos.ps1 | Kerberos enabled; app auto-created
P3 | 3.2 | FSLogix profile container | session-host | session-host | .\scripts\configure-fslogix.ps1 | Profile mounts from share on logon
PHASE 4 - SESSION HOST
P4 | 4.1 | Session host joined to host pool | admin-pc | host pool | Get-AzWvdSessionHost -HostPoolName hp-avd-lab | Status = Available
P4 | 4.2 | User connects to desktop | client | AVD | Connect via Windows App / web client | Desktop launches; SSO; profile loads